## Sheet1
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Conceptual & Facilities Design
Architectural Contract
Conceptual Drawing
Floor Plan & Elevations
Kitchen Drawing
Dining Room/Bar Design
Interior Design & Finishes
Landscape Design
Kitchen Designer Contract
Restaurant Cons. Contract
Construction
Construction Contract
Sub-Contractor List
Obtain Permits
Concrete Work
Structural Repairs
Wall Framing
Bar Framing
Plumbing Rough-In
HVAC Rough-In
Electrical Rough-In
Plaster Repairs
Sheet Rock
Storefront
Doors
Painting
Cabinetry
M, P & E Trim-out
Equipment Hookup
Bathroom Accessories
Final Inspections
Clean-up/Punch-out
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Licensing & Permitting
Liquor, Beer & Wine
State
County/City
Business License
Sales & Use Tax ID #
Impact Fees
Health Department Permit
Food Service Permit
Fire Marshal Inspection
Certificate of Occupancy
Service Contracts
Pest Control
Hood Cleaning
Garbage Removal
Recycables
Utilities
Electricity
Gas
Water & Sewer
Telephone
Linen Service
Elect. Systems/Hardware
POS Selection
Data Base Construction
Menu
Bar
Modifiers
Mgt. Training Schedule
Equipment ck/maint.
Emp. Training Schedule
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
POS Supp./Crash Kit
PC Selection
Sound System
Telephone Service
Restaurant System
Pay Phones
Bypass
Computer/Modem Line
Locks and Keys
F, F & E Selection
Kitchen Equipment
Fire Protection
Dining Room Smallwares
Kitchen Smallwares
Bar Smallwares
Dining Rm Tables & Chairs
Dining Rm Booths
Booth Fabric
Bar Tables & Chairs
Outdoor Furniture
Tabletop (China,Flat,Stem)
Custom Lighting
Art Work & Accessories
Custom Door Hardware
Office Equipment
Office Supply
Company Imaging & Design
Name Selection
Logo Development
Menu & Wine List Design
Retail Merch. Design
Uniform Design
Signage Design
Misc. Collateral Design
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Menu & Beverage Development
Menu
R&D
Menu Drafts
Final Drafts
Recipe Development
Menu Pricing
Test Kitchen
Menu Descriptions
Plating Guides
Costing & Theoreticals
Ordering Forms
Inventory Forms
Vendor List
Beverage
R&D
Wine List
Wine Tasting
Final Wine Selection
Pricing
Wine List Pricing
Beer Program
Liquor Program
Speciality Drinks
Coffee Program
Beverage Opening Order
Beverage Order Forms
Bev. Inventory Forms
Bar Opening Checklist
Bar Closing Checklist
Bar Seq. of Service
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Employee Development
Pre-Opening Staffing Guide
Employee Manual
Draft
Final Draft
Training Format
Service Sequence
Training Manual
Opening/Closing Checklist
Daily,Weekly,Monthly Cleaning Checklists
Kitchen
Bar
Dining Room
Uniforms
Dining Room
Hostess
Bar
Kitchen
Stewards/ SA's
Staff Hiring
Interview Schedule
Training Schedule
Testing Schedule
Employee New Hire Packet
Applications
W-4
I-9
Insurance
Employee Handbook
Map of Restaurant
Restaurant Fact Sheet
|  | Month 1 |  |  |  | Month 2 |  |  |  | Month 3 |  |  |  | Month 4 |  |  |  | Month 5 |  |  |  | Month 6
Activity | Resp Party | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
Financial & Administrative
Policies & Procedures
Pre-Opening Budget
Operating Budget
Banking
Accounts Set-Up
Signature Cards
Checks Ordered
Credit Cards
Purveyor Credit Applications
Rates Negotiated
Account Numbers
imprinters
Miscellaneous
Accounting Set-Up
AP/AR
Payroll Set-Up
Daily Cash Control Procedures
Weekly Management Report